## Stakeholder Register
ID | Stakeholder | Role | Needs | Responsibilities | Interest | Influence | Communication | Engagement Strategy | Priority
ST-01 | Student | Internship applicant and participant | Find internships, apply, track applications and submit reports | Maintain profile, apply, complete tasks, submit reports and respond to feedback | High | High | Notifications, email, dashboard, feedback forms | Manage closely | Critical
ST-02 | Company | Internship provider | Publish internships and manage applications | Create opportunities, review applications, participate in selection | High | High | Email, notifications, dashboard, meetings | Manage closely | Critical
ST-03 | Company Supervisor | Workplace supervisor | Monitor student workplace activities | Assign tasks, monitor progress, provide feedback and evaluation | High | Medium | Notifications, task dashboard, feedback forms | Keep informed / closely involved | High
ST-04 | University Coordinator | Internship placement and coordination manager | Manage placements and approvals | Review opportunities, coordinate placements, approve applications and assign supervisors | High | High | Dashboard, reports, meetings, email | Manage closely | Critical
ST-05 | University Supervisor | Academic supervisor | Monitor academic progress and evaluate students | Review reports, monitor progress, provide guidance and evaluate students | High | Medium | Notifications, reports, meetings, feedback forms | Keep closely involved | High
ST-06 | System Administrator | System and user administrator | Manage users, roles and system configuration | Manage accounts, permissions, configuration, security and technical support | High | High | Admin dashboard, alerts, reports, meetings | Manage closely | Critical

## Power-Interest Matrix
interest
| low | high
high power | keep
low power | Monitor
MANAGE CLOSELY
Student
Company
Coordinator
Adminstrator
KEEP INFORMED
Company
Supervisor
University
Supervisor

## Stakeholder Engagement
Stakeholder | Current Engagement | Desired Engagement | Gap | Action
Student | Consulted | Actively involved | Medium | Conduct interviews and usability testing
Company | Consulted | Actively involved | Medium | Collect employer requirements
Company Supervisor | Informed | Actively involved | Medium | Gather monitoring and evaluation requirements
University Coordinator | Actively involved | Actively involved | Low | Conduct requirement workshops
University Supervisor | Consulted | Actively involved | Medium | Gather academic monitoring requirements
System Administrator | Actively involved | Actively involved | Low | Discuss security and administration requirements

## Stakeholder_Requirements
Requirement ID | Stakeholder | Requirement | Priority
REQ-001 | Student | Student shall be able to create and update profile | High
REQ-002 | Student | Student shall be able to search internships | High
REQ-003 | Student | Student shall be able to submit applications | High
REQ-004 | Student | Student shall be able to track application status | High
REQ-005 | Company | Company shall be able to publish internships | High
REQ-006 | Company | Company shall be able to review applications | High
REQ-007 | Company Supervisor | Supervisor shall be able to assign tasks | High
REQ-008 | Company Supervisor | Supervisor shall be able to provide feedback | Medium
REQ-009 | University Coordinator | Coordinator shall be able to approve placements | High
REQ-010 | University Supervisor | Supervisor shall be able to review reports | High
REQ-011 | University Supervisor | Supervisor shall be able to evaluate students | High
REQ-012 | Administrator | Administrator shall manage users and roles | High